## Product Backlog
Project Name | saucedemo
Client | ExcelR
Created By | Aditi,Chandini,Aruna,Bhavani,Ajaykumar,Shamshannisha,Priyanka
Creation Date | 2024-06-14
Approval Date
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Creteria
Epic-1 | US_01 | Verify the visibility and accessibility of "add to cart" button on the product page. | ADD TO CART button is displayed. | Done | 1.ADD TO CART button is visible on the product page. 2.ADD TO CART button is labeled clearly and is positioned correctly. 3.ADD TO CART button meets accessibility standards.
| US_02 | Verify that the "Add to Cart" button is clickable and adds items to the cart. | ADD TO CART button is functionable . | Done | 1. Add to cart button is clickable and responsive to usert interactions. 2.Clicking "Add to cart" button adds selected item to cart. 3.The cart count updates immediately upon successful addition of item in cart.
| US_03 | Verify that add to cart image shows count of items it contains. | Add To Cart icon indicates count of items in it. | Done | 1.The cart icon is visible on all pages and displays the count of items it contains. 2.The item count updates accurately and immediately when items are added or removed from the cart.
| US_04 | Verify that items added to the cart opens product details page after clicking on the items in the cart | Product details page is displayed | Done | 1.Items added to the cart are listed under the cart section or icon. 2.Clicking on an item within the cart navigates the user to the product details page. 3.The product details page displays accurate information about the selected item.
| US_05 | Verify that the "Add to Cart" button changes to remove button after adding item to cart. | Update of Remove button after adding product to cart. | Done | 1.After adding an item to the cart, the "Add to Cart" button changes to a "Remove" button or similar functionality. 2.The "Remove" button is clearly labeled and positioned where the "Add to Cart" button was. 3.Clicking the "Remove" button successfully removes the item from the cart and updates the cart count.
| US_06 | Verify that items can be successfully removed from and re-added to the cart without errors. | Items are removed and re-added back | Done | 1.Items are removable from the cart using the "Remove" button or similar functionality. 2.Removing an item updates the cart count accurately and reflects the change in the cart. 3.Items are re-addable to the cart without errors, and the cart count updates accordingly.
| US_07 | Verify that add to cart icon is responsive and opens your cart page after clicking. | My Cart page by clicking on add to cart icon. | Done | 1.The cart icon is responsive and functional across different devices and screen sizes. 2.Clicking on the cart icon navigates the user to the cart page. 3.The cart page displays all items added to the cart accurately, regardless of the device used.
| US_08 | Verify that product details is displayed by clicking on the product image in home page. | Product details page accessable from home page. | Done | 1.When the user clicks on a product image on the product listing page, the product details page is displayed. 2.The product details page shows comprehensive information about the product, including images, descriptions, specifications, pricing, and availability.
| US_09 | Verify the back button in product details page returns to home page. | Functionality of Back button in product details page. | Done | 1.The product details page includes a back button that is clearly visible and labeled. 2.Clicking the back button navigates the user back to the home page. 3.The home page should retain the user's previous state (e.g., scroll position, filters) to provide a seamless browsing experience.
| US_10 | To verify the login functionality of valid user id and lower case characters of password | A pop up box of an error message will be displayed | Done | 1.Enter valid user id and invalid password. 2.Click on login button. 3.A pop box of an error message.
| US_11 | To verify the login functionality of valid user id and special characters of password | A pop up box of an error message will be displayed | Done | 1.Enter the Valid user id and valid password. 2.Click on login button. 3.A pop box of an error message.
| US_12 | To verify the login functionality of valid user id and uppercase characters of password | A pop up box of an error message will be displayed | Done | 1.Enter the valid user and invalid password. 2.click on the login button. 3.A pop up box of an error message.
| US_13 | To verify the login funtionaltiy of invalid user id and invalid password | A pop up box of an error message will be displayed | Done | 1.Enter the invalid user id and invalid password. 2.click on the login button. 3.A pop up box of an error message.
| US_14 | TO verify the login functionality of the invalid user id and valid password | A pop up box of an error mesaage will be displayed | Done | 1.Enter the invalid user id and valid password. 2.click on login button. 3 .A pop up box of error message
| US_15 | To verify the login functionality of the valid user id and valid password | Land on home page and able to see the products | Done | 1.Enter valid user id and password. 2.click on the login button. 3.navigate to home page.
| US_16 | verify the login funtionaltiy when a user enter lower case characters of user id and valid password | A pop up box of an Error message will be displayed | Done | 1.Enter invalid user id and valid password. 2.click on login button. 3.A pop up box of error message.
| US_17 | to verify the login functionality of the valid user id and invalid password | A pop up box of an error message will be displayed | Done | 1.enter the valid id and invalid password 2.click on login button 3.A pop up box of an error message
| US_18 | To verify the login functionality with special characters of user id and valid password | A pop up box of an error message will be displayed | Done | 1.Enter the invalid user id and valid password 2.click on login button 3.A pop up box of an error message
| US_19 | To verify the login funtionaltiy of numeric user id and valid password | A pop up box an error message will be displayed | Done | 1.enter the invalid user id and valid password. 2.click on login button 3.A pop up box of an error message.
| US_20 | Verify the login functionality of saucedemo when a valid username and invalid password | Username and password do not match any user in this service | Done | 1.Open the saucedemo application 2. Enter a invalid username 3.Enter valid password. 4.Click on login button.
| US_21 | Verify the login functionality of Saucedemo with invalid Username and valid password. | Username and password do not match any user in this service | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter invalid password. 4.Click on login button.
| US_22 | Verify the login functionality of Saucedemo with invalid Username and invalid password. | Username and password do not match any user in this service | Done | 1.open the saucedemo application 2. Enter a invalid Username 3.Enter invalid password. 4.Click on login button.
| US_23 | Verify the login functionality of Saucedemo with valid Username and valid password. | User should landed on the home page and to see the products. | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Click on login button.
| US_24 | Verify the login functionality of Saucedemo with Username is empty and valid password. | Username is Required | Done | 1.open the saucedemo application 2.Leave the Username field empty. 3.Enter valid password. 4.Click on login button.
| US_25 | Verify the login functionality of Saucedemo with valid username and empty password. | Password is Required | Done | 1.open the saucedemo application 2.Enter a valid Username 3.Leave the password field empty. 4.Click on login button.
| US_26 | Verify the Login Button Accessibility. | User should click on login button and landed on the home page and to see the products. | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Check if the login button is clickable.
| US_27 | Verify the Home page functionality of Saucedemo as View Product Catalog. | A product should be displayed each with an image, name, price, and Description. | Done | 1. Login to the Saucedemo application. 2. Observe the product catalog on the dashboard.
| US_28 | Verify the Home page functionality of Saucedemo as Product Add to Cart. | The product should be added to the cart, and the cart icon should display the updated number of items. | Done | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product.
| US_29 | Verify the Home page functionality of Saucedemo as Remove product from cart. | The product should be Remove from the cart and the cart icon should update accordingly. | Done | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product. 3. Click on the cart icon. 4. Click the "Remove" button next to the product.
| US_30 | Verify the Home page functionality of Saucedemo as Filter Product by Price. | "Product should be sorted by price from low to high." | Done | 1. Login to the Saucedemo application. 2.Click on the filter dropdown. 3. Select "Price(low to high)".
| US_31 | Verify the cart functionality of Saucedemo as Checkout Process. | "The user should be able to complete the checkout process and receive an order conformation." | Done | 1. Login to the Saucedemo application. 2. Add one or more products to the cart. 3. Click on the Cart icon. 4. click The "Checkout" Button. 5. Enter Firsrt Name, Last Name, Postalcode. 6. Click on the Continue Button. 7. Click on the Finish Button. 8. confirm the order.
| US_32 | Verify the Logout Functionality of Saucedemo. | "The user should be logged out and redirected to the login page." | Done | 1. Login to the Saucedemo application. 2. Click on the menu button. 3. Click the "Logout" button.
| US_33 | Verify the checkout button is it visible and clickable . | On clicking Checkout button user should land on your Information Page. | Done | 1. Click on Checkout button 2. User is redirected to Your Information page
| US_34 | Verify the Checkout functionality when the user enter valid First name, Last Name and ZipPostal Code | User should redirected to Overview page | Done | 1. Enter valid Fist Name, Last Name, and ZipPostal Code. 2. Click on the Continue button. 3. User is redirected to OverView page.
| US_35 | Verify the Checkout functionality when the user enter Numeric data in First Name, Character data in Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Enter Numeric in First Name, Characters in Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of an error message is not displayed.
| US_36 | Verify the Checkout functionality when the user enter Numeric data in Last Name, Character data in First Name and ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Enter Numeric in Last Name, Characters in First Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_37 | Verify the Checkout functionality when the user enter character data in First Name, Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Enter characters in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_38 | Verify the Checkout functionality when the user enter Numeric data in First Name, Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Enter Numerics in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_39 | Verify the Checkout functionality when the user enter Numeric data in First Name and Last Name, Characters data in ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Enter Numerics in First Name and Last Name, Characters in ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_40 | Verify the Checkout functionality when the user do not enter any data in First Name, Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | Done | 1. Do not enter any value in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is displayed.
| US_41 | Verify the Cancel button of Checkout Page is visible and clickable. | User should be redirected to Your Cart page | Done | 1. Click on Cancle button. 2. User is redirected to Your Cart page.
| US_42 | Verify the Finish button of Overview Page is visible and clickable. | User should redirected to Finish page and user should see Thank You message. | Done | 1. Click on Finish button. 2. User is redirected to Finish page and Thank You message is displayed.
| US_43 | verify the login functionality with valid details | Users should be able to log in using their username and password to access their account | Done | 1.The login page should be accessible from the homepage. 2.Users should be able to enter a valid username and password. 3.Clicking the login button with valid credentials should redirect the user to the inventory page.
| US_44 | verify the login functionality with invalid details. | Users should not able to login using invalid username and password | Done | 1.The login page should be accessible from the homepage. 2.Users should be able to enter a valid username and password. 3.An error message should be displayed if the user enters invalid credentials.
| US_45 | verify the add to cart functionality | Users should be able to add products to their shopping cart from the inventory page. | Done | 1.The inventory page should display a list of available products. 2.Each product should have an "Add to cart" button. Clicking the "Add to cart" button should add the item to the cart. 3.The cart icon should display the correct number of items added. 4.The item should appear in the cart when viewed.
| US_46 | To verify that an item can be removed from the cart | Users should be able to remove products from their shopping cart. | Done | 1.The cart page should display a list of items added to the cart. 2.Each item should have a "Remove" button. 3.Clicking the "Remove" button should remove the item from the cart. 4.The cart icon should update to reflect the correct number of remaining items. 5.The item should no longer appear in the cart when viewed.
| US_47 | To Verify that product details can be viewed. | Users should be able to view detailed information about a product. | Done | 1.The inventory page should display a list of products with titles and images. 2.Clicking on a product title should navigate to the product details page. 3.The product details page should display the product's image, price, and description. 4.The information displayed should match the selected product.
| US_48 | To Verify that products can be sorted by different criteria. | Users should be able to sort products by price, name, etc. | Done | 1.The inventory page should have a sort dropdown menu. 2.Users should be able to select sorting criteria (e.g., "Price (low to high)", "Name (A to Z)"). 3.The products should be rearranged according to the selected sorting criteria. 4.The sorting should be accurate and consistent.
| US_49 | To Verify that a user can complete the checkout process. | Users should be able to enter their information and complete the purchase. | Done | 1.The cart page should have a "Checkout" button. Clicking the "Checkout" button should navigate to the checkout information page. 2.Users should be able to enter their first name, last name, and postal code. 3.Clicking the "Continue" button should navigate to the order overview page. 4.Clicking the "Finish" button should complete the purchase and display an order confirmation page. 5.The order confirmation page should display a success message and order details.
| US_50 | To Verify that the correct message is displayed when the cart is empty. | Users should receive feedback when their cart is empty. | Done | 1.The cart page should be accessible and display any added items. 2.If no items are added to the cart, the cart page should display a message indicating that the cart is empty. 3.The message should be clear and user-friendly.
| US_51 | To verify the responsive design of the sauce demo | The website should be usable on various devices with different screen sizes. | Done | 1.The website should be accessible and functional on various devices (desktop, tablet, mobile). 2.The layout should adjust appropriately for different screen sizes. 3.Key functionalities (e.g., login, add to cart) should be usable across all devices. 4.The design should maintain usability and accessibility standards.
| US_52 | To Verify that a user can log out successfully. | Users should be able to log out and be redirected to the login page. | Done | 1.The inventory page should have a menu button to access the logout option. 2.Clicking the menu button should display a logout option. 3.Clicking the logout option should log the user out and redirect them to the login page. 4.No user-specific information should be accessible after logout.
| US_63 | Verify the login functionality when a user enter valid username and valid password. | User able to see the home page and start shopping. | Done | 1.Enter valid username & valid password 2.Click on login button
| US_64 | Verify the login functionality when a user enter valid username and invalid password. | Want to see appropriate feedback when an incorrect password is entered during login. | Done | 1.Enter valid username & invalid password 2.Click on login button
Epic-1 | US_65 | Verify that the menu icon is clickable and it displays options including All items and About | The menu icon should be clickable and should display certain options. | Done | 1.Navigate to the top left corner of the page where menu icon is displayed. 2. Click on menu icon to display certain options.
| US_66 | Verify that "All Items" is clickable in Menu. | The "All Items" option should be clickable and should be redirect to inventory page. | Done | 1. Navigate to the Menu bar in page. 2. Click on Menu Bar to display certain options.
| US_67 | Verify that "About" is clickable in Menu. | The "About" option should be clickable and should be redirect to saucelabs website. | Done | 1. Navigate to the Menu bar in page. 2. Click on Menubar to display certain options.
| US_68 | Verify the checkout functionality. | The "Checkout" option should be displayed and clickable on cart page. | Done | 1.Click on the "Cart" icon to see "Checkout" option in cart page. 2.The Checkout should be redirect to checkout-step-one page.
| US_69 | Verify that checkout-step-one page has a form for user details. | The form should be displayed. | Done | 1.User can fill the form with all details. 2.User can not continue with blank fields.
| US_70 | Verify that the filter icon is present and clickable in the product page | The filter icon should be present and clickable on the top right corner of the product page | Done | 1. After successful login, Click on the filter icon present in the top right corner of the product page 2. The filter icon should display the drop-down options such as Name(A to Z), Name(Z to A), Price(low to high), price(high to low)
| US_71 | Verify that the products are displayed in alphabetical order from A to Z based on product name in the product page | The products should be displayed in alphabetical order from A to Z based on product name in the product page when the Name(A to Z) option is clicked in the filter drop-down options | Done | 1. After successful login, Click on the filter icon present in the top right corner of the product page 2. Click on the Name(A to Z) from the drop-down option of the filter icon. The products should be displayed based on the alphabetical order of the product names

## Sprint Planning
Project Name | Saucedemo
Client | Excel R
Created By | Aditi,Chandini,Aruna,Bhavani,Ajaykumar,Shamshannisha,Priyanka
Attendees | Aditi,Chandini,Aruna,Bhavani,Ajaykumar,Shamshannisha,Priyanka
Creation Date | 2024-06-14
Epic | User Story ID | Feature/Title | User Story | Sprint | Status | Acceptance Creteria
Epic-1 | US_01 | Verify the visibility and accessibility of "add to cart" button on the product page. | ADD TO CART button is displayed. | 1 | Done | 1.ADD TO CART button is visible on the product page. 2.ADD TO CART button is labeled clearly and is positioned correctly. 3.ADD TO CART button meets accessibility standards.
| US_02 | Verify that the "Add to Cart" button is clickable and adds items to the cart. | ADD TO CART button is functionable . | 1 | Done | 1. Add to cart button is clickable and responsive to usert interactions. 2.Clicking "Add to cart" button adds selected item to cart. 3.The cart count updates immediately upon successful addition of item in cart.
| US_03 | Verify that add to cart image shows count of items it contains. | Add To Cart icon indicates count of items in it. | 1 | Done | 1.The cart icon is visible on all pages and displays the count of items it contains. 2.The item count updates accurately and immediately when items are added or removed from the cart.
| US_04 | Verify that items added to the cart opens product details page after clicking on the items in the cart | Product details page is displayed | 1 | Done | 1.Items added to the cart are listed under the cart section or icon. 2.Clicking on an item within the cart navigates the user to the product details page. 3.The product details page displays accurate information about the selected item.
| US_05 | Verify that the "Add to Cart" button changes to remove button after adding item to cart. | Update of Remove button after adding product to cart. | 1 | Done | 1.After adding an item to the cart, the "Add to Cart" button changes to a "Remove" button or similar functionality. 2.The "Remove" button is clearly labeled and positioned where the "Add to Cart" button was. 3.Clicking the "Remove" button successfully removes the item from the cart and updates the cart count.
| US_06 | Verify that items can be successfully removed from and re-added to the cart without errors. | Items are removed and re-added back | 1 | Done | 1.Items are removable from the cart using the "Remove" button or similar functionality. 2.Removing an item updates the cart count accurately and reflects the change in the cart. 3.Items are re-addable to the cart without errors, and the cart count updates accordingly.
| US_07 | Verify that add to cart image is responsive and opens your cart page after clicking. | My Cart page by clicking on add to cart icon. | 1 | Done | 1.The cart icon is responsive and functional across different devices and screen sizes. 2.Clicking on the cart icon navigates the user to the cart page. 3.The cart page displays all items added to the cart accurately, regardless of the device used.
| US_08 | Verify that product details is displayed by clicking on the product image in home page. | Product details page accessable from home page. | 1 | Done | 1.When the user clicks on a product image on the product listing page, the product details page is displayed. 2.The product details page shows comprehensive information about the product, including images, descriptions, specifications, pricing, and availability.
| US_09 | Verify the back button in product details page returns to home page. | Functionality of Back button in product details page. | 1 | Done | 1.The product details page includes a back button that is clearly visible and labeled. 2.Clicking the back button navigates the user back to the home page. 3.The home page should retain the user's previous state (e.g., scroll position, filters) to provide a seamless browsing experience.
| US_10 | To verify the login functionality of valid user id and lower case characters of password | A pop up box of an error message will be displayed | 2 | Done | 1.Enter valid user id and invalid password. 2.Click on login button. 3.A pop box of an error message.
| US_11 | To verify the login functionality of valid user id and special characters of password | A pop up box of an error message will be displayed | 2 | Done | 1.Enter the Valid user id and valid password. 2.Click on login button. 3.A pop box of an error message.
| US_12 | To verify the login functionality of valid user id and uppercase characters of password | A pop up box of an error message will be displayed | 2 | Done | 1.Enter the valid user and invalid password. 2.click on the login button. 3.A pop up box of an error message.
| US_13 | To verify the login funtionaltiy of invalid user id and invalid password | A pop up box of an error message will be displayed | 2 | Done | 1.Enter the invalid user id and invalid password. 2.click on the login button. 3.A pop up box of an error message.
| US_14 | TO verify the login functionality of the invalid user id and valid password | A pop up box of an error mesaage will be displayed | 2 | Done | 1.Enter the invalid user id and valid password. 2.click on login button. 3 .A pop up box of error message
| US_15 | To verify the login functionality of the valid user id and valid password | Land on home page and able to see the products | 2 | Done | 1.Enter valid user id and password. 2.click on the login button. 3.navigate to home page.
| US_16 | verify the login funtionaltiy when a user enter lower case characters of user id and valid password | A pop up box of an Error message will be displayed | 2 | Done | 1.Enter invalid user id and valid password. 2.click on login button. 3.A pop up box of error message.
| US_17 | to verify the login functionality of the valid user id and invalid password | A pop up box of an error message will be displayed | 2 | Done | 1.enter the valid id and invalid password 2.click on login button 3.A pop up box of an error message
| US_18 | To verify the login functionality with special characters of user id and valid password | A pop up box of an error message will be displayed | 2 | Done | 1.Enter the invalid user id and valid password 2.click on login button 3.A pop up box of an error message
| US_19 | To verify the login funtionaltiy of numeric user id and valid password | A pop up box an error message will be displayed | 2 | Done | 1.enter the invalid user id and valid password. 2.click on login button 3.A pop up box of an error message.
| US_20 | Verify the login functionality of saucedemo when a valid username and invalid password | Username and password do not match any user in this service | 3 | Done | 1.Open the saucedemo application 2. Enter a invalid username 3.Enter valid password. 4.Click on login button.
| US_21 | Verify the login functionality of Saucedemo with invalid Username and valid password. | Username and password do not match any user in this service | 3 | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter invalid password. 4.Click on login button.
| US_22 | Verify the login functionality of Saucedemo with invalid Username and invalid password. | Username and password do not match any user in this service | 3 | Done | 1.open the saucedemo application 2. Enter a invalid Username 3.Enter invalid password. 4.Click on login button.
| US_23 | Verify the login functionality of Saucedemo with valid Username and valid password. | User should landed on the home page and to see the products. | 3 | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Click on login button.
| US_24 | Verify the login functionality of Saucedemo with Username is empty and valid password. | Username is Required | 3 | Done | 1.open the saucedemo application 2.Leave the Username field empty. 3.Enter valid password. 4.Click on login button.
| US_25 | Verify the login functionality of Saucedemo with valid username and empty password. | Password is Required | 3 | Done | 1.open the saucedemo application 2.Enter a valid Username 3.Leave the password field empty. 4.Click on login button.
| US_26 | Verify the Login Button Accessibility. | User should click on login button and landed on the home page and to see the products. | 3 | Done | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Check if the login button is clickable.
| US_27 | Verify the Home page functionality of Saucedemo as View Product Catalog. | A product should be displayed each with an image, name, price, and Description. | 3 | Done | 1. Login to the Saucedemo application. 2. Observe the product catalog on the dashboard.
| US_28 | Verify the Home page functionality of Saucedemo as Product Add to Cart. | The product should be added to the cart, and the cart icon should display the updated number of items. | 3 | Done | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product.
| US_29 | Verify the Home page functionality of Saucedemo as Remove product from cart. | The product should be Remove from the cart and the cart icon should update accordingly. | 3 | Done | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product. 3. Click on the cart icon. 4. Click the "Remove" button next to the product.
| US_30 | Verify the Home page functionality of Saucedemo as Filter Product by Price. | "Product should be sorted by price from low to high." | 3 | Done | 1. Login to the Saucedemo application. 2.Click on the filter dropdown. 3. Select "Price(low to high)".
| US_31 | Verify the cart functionality of Saucedemo as Checkout Process. | "The user should be able to complete the checkout process and receive an order conformation." | 3 | Done | 1. Login to the Saucedemo application. 2. Add one or more products to the cart. 3. Click on the Cart icon. 4. click The "Checkout" Button. 5. Enter Firsrt Name, Last Name, Postalcode. 6. Click on the Continue Button. 7. Click on the Finish Button. 8. confirm the order.
| US_32 | Verify the Logout Functionality of Saucedemo. | "The user should be logged out and redirected to the login page." | 3 | Done | 1. Login to the Saucedemo application. 2. Click on the menu button. 3. Click the "Logout" button.
| US_33 | Verify the checkout button is it visible and clickable. | On clicking Checkout button user should see User Information Page. | 1 | Done | 1. Click on Checkout button 2. User is redirected to User Information page
| US_34 | Verify the Checkout functionality when the user enter valid First name, Last Name and ZipPostal Code | User should redirected to Overview page | 1 | Done | 1. Enter valid Fist Name, Last Name, and ZipPostal Code. 2. Click on the Continue button. 3. User is redirected to OverView page.
| US_35 | Verify the Checkout functionality when the user enter Numeric data in First Name, Characters data in Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | 1 | Done | 1. Enter Numeric in First Name, Characters in Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of an error message is not displayed.
| US_36 | Verify the Checkout functionality when the user enter Numeric data in Last Name, Characters data in First Name and ZipPostal Code. | A Popup box of an error message should be displayed. | 1 | Done | 1. Enter Numeric in Last Name, Characters in First Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_37 | Verify the Checkout functionality when the user enter characters data in First Name, Last Name and ZipPostal Code | A Popup box of an error message should be displayed. | 1 | Done | 1. Enter characters in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_38 | Verify the Checkout functionality when the user enter Numeric data in First Name, Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | 1 | Done | 1. Enter Numerics in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_39 | Verify the Checkout functionality when the user enter Numerics data in First Name and Last Name, Characters data in ZipPostal Code. | A Popup box of an error message should be displayed. | 1 | Done | 1. Enter Numerics in First Name and Last Name, Characters in ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is not displayed.
| US_40 | Verify the Checkout functionality when the user do not enter any data in First Name, Last Name and ZipPostal Code. | A Popup box of an error message should be displayed. | 1 | Done | 1. Do not enter any value in First Name, Last Name and ZipPostal Code. 2. Click on the Continue button. 3. A Popup box of error message is displayed.
| US_41 | Verify the Cancel button of Checkout Page is visible and Clickable. | User should be redirected to Your Cart page | 1 | Done | 1. Click on Cancle button. 2. User is redirected to Your Cart page.
| US_42 | Verify the Finish button of Overview Page is Visible and Clickable. | User should redirected to Finish page and user should see Thank You message. | 1 | Done | 1. Click on Finish button. 2. User is redirected to Finish page and Thank You message is displayed.
| US_43 | verify the login functionality with valid details | Users should be able to log in using their username and password to access their account | 2 | Done | 1.The login page should be accessible from the homepage. 2.Users should be able to enter a valid username and password. 3.Clicking the login button with valid credentials should redirect the user to the inventory page.
| US_44 | verify the login functionality with invalid details. | Users should not able to login using invalid username and password | 2 | Done | 1.The login page should be accessible from the homepage. 2.Users should be able to enter a valid username and password. 3.An error message should be displayed if the user enters invalid credentials.
| US_45 | verify the add to cart functionality | Users should be able to add products to their shopping cart from the inventory page. | 2 | Done | 1.The inventory page should display a list of available products. 2.Each product should have an "Add to cart" button. Clicking the "Add to cart" button should add the item to the cart. 3.The cart icon should display the correct number of items added. 4.The item should appear in the cart when viewed.
| US_46 | To verify that an item can be removed from the cart | Users should be able to remove products from their shopping cart. | 2 | Done | 1.The cart page should display a list of items added to the cart. 2.Each item should have a "Remove" button. 3.Clicking the "Remove" button should remove the item from the cart. 4.The cart icon should update to reflect the correct number of remaining items. 5.The item should no longer appear in the cart when viewed.
Epic | US_47 | To Verify that product details can be viewed. | Users should be able to view detailed information about a product. | 2 | Done | 1.The inventory page should display a list of products with titles and images. 2.Clicking on a product title should navigate to the product details page. 3.The product details page should display the product's image, price, and description. 4.The information displayed should match the selected product.
| US_48 | To Verify that products can be sorted by different criteria. | Users should be able to sort products by price, name, etc. | 2 | Done | 1.The inventory page should have a sort dropdown menu. 2.Users should be able to select sorting criteria (e.g., "Price (low to high)", "Name (A to Z)"). 3.The products should be rearranged according to the selected sorting criteria. 4.The sorting should be accurate and consistent.
| US_49 | To Verify that a user can complete the checkout process. | Users should be able to enter their information and complete the purchase. | 2 | Done | 1.The cart page should have a "Checkout" button. Clicking the "Checkout" button should navigate to the checkout information page. 2.Users should be able to enter their first name, last name, and postal code. 3.Clicking the "Continue" button should navigate to the order overview page. 4.Clicking the "Finish" button should complete the purchase and display an order confirmation page. 5.The order confirmation page should display a success message and order details.
| US_50 | To Verify that the correct message is displayed when the cart is empty. | Users should receive feedback when their cart is empty. | 2 | Done | 1.The cart page should be accessible and display any added items. 2.If no items are added to the cart, the cart page should display a message indicating that the cart is empty. 3.The message should be clear and user-friendly.
| US_51 | To verify the responsive design of the sauce demo | The website should be usable on various devices with different screen sizes. | 2 | Done | 1.The website should be accessible and functional on various devices (desktop, tablet, mobile). 2.The layout should adjust appropriately for different screen sizes. 3.Key functionalities (e.g., login, add to cart) should be usable across all devices. 4.The design should maintain usability and accessibility standards.
| US_52 | To Verify that a user can log out successfully. | Users should be able to log out and be redirected to the login page. | 2 | Done | 1.The inventory page should have a menu button to access the logout option. 2.Clicking the menu button should display a logout option. 3.Clicking the logout option should log the user out and redirect them to the login page. 4.No user-specific information should be accessible after logout.
| US_63 | Verify the login functionality when a user enter valid username and valid password. | User able to see the home page and start shopping. | 1 | Done | 1.Enter valid username & valid password 2.Click on login button
| US_64 | Verify the login functionality when a user enter valid username and invalid password. | want to see appropriate feedback when an incorrect password is entered during login. | 1 | Done | 1.Enter valid username & invalid password 2.Click on login button
| US_65 | Verify that the menu icon is clickable and it displays options including All items and About | The menu icon should be clickable and should display certain options. | 1 | Done | 1.Navigate to the top left corner of the page where menu icon is displayed. 2. Click on menu icon to display certain options.
| US_66 | Verify that "All Items" is clickable in Menu. | The "All Items" option should be clickable and should be redirect to inventory page. | 1 | Done | 1. Navigate to the Menu bar in page. 2. Click on Menu Bar to display certain options.
| US_67 | Verify that "About" is clickable in Menu. | The "About" option should be clickable and should be redirect to saucelabs website. | 1 | Done | 1. Navigate to the Menu bar in page. 2. Click on Menubar to display certain options.
| US_68 | Verify the checkout functionality. | The "Checkout" option should be displayed and clickable on cart page. | 1 | Done | 1.Click on the "Cart" icon to see "Checkout" option in cart page. 2.The Checkout should be redirect to checkout-step-one page.
| US_69 | Verify that checkout-step-one page has a form for user details. | The form should be displayed. | 1 | Done | 1.User can fill the form with all details. 2.User can not continue with blank form. 3.User can not continue with blank fields.
| US_70 | Verify that the filter icon is present and clickable in the product page | The filter icon should be present and clickable on the top right corner of the product page | 1 | Done | 1. After successful login, Click on the filter icon present in the top right corner of the product page 2. The filter icon should display the drop-down options such as Name(A to Z), Name(Z to A), Price(low to high), price(high to low)
| US_71 | Verify that the products are displayed in alphabetical order from A to Z based on product name in the product page | The products should be displayed in alphabetical order from A to Z based on product name in the product page when the Name(A to Z) option is clicked in the filter drop-down options | 1 | Done | 1. After successful login, Click on the filter icon present in the top right corner of the product page 2. Click on the Name(A to Z) from the drop-down option of the filter icon. The products should be displayed based on the alphabetical order of the product names

## Test scenarios
,
Project Name | Saucedemo
Module Name | Saucedemo_Test_cases
Requirement Number | REQ001
Test case Type | Functionality , Usability , compatibility Testings
Reference Doccument | NA
Pre-condition | Saucedemo URL should be accessible
Test Data | https://www.saucedemo.com/
Test Senario number | Description | Test Scenario Type | TE Name
User Story 1- Shamshannisha
TSH_01 | Verify the visibility and accessibility of "add to cart" button on the product page. | Functional Testing | Shamshannisha
TSH_02 | Verify that the "Add to Cart" button is clickable and adds items to the cart. | Functional Testing | Shamshannisha
TSH_03 | Verify that add to cart image shows count of items it contains. | Functional Testing | Shamshannisha
TSH_04 | Verify that items added to the cart opens product details page after clicking on the items in the cart | Functional Testing | Shamshannisha
TSH_05 | Verify that the "Add to Cart" button changes to remove button after adding item to cart. | Functional Testing | Shamshannisha
TSH_06 | Verify that items can be successfully removed from and re-added to the cart without errors. | Functional Testing | Shamshannisha
TSH_07 | Verify that add to cart image is responsive and opens your cart page after clicking. | Functional Testing | Shamshannisha
TSH_08 | Verify that product details is displayed by clicking on the product image in home page. | Functional Testing | Shamshannisha
TSH_09 | Verify the back button in product details page returns to home page. | Functional Testing | Shamshannisha
User Story 2- Chandini Appikonda
TSH_10 | verify the login functionality of valid user id and lower case charachters of password | Functional Testing | CHANDINI APPIKONDA
TSH_11 | verify the login functionality of valid user id and specail characters of password | Functional Testing | CHANDINI APPIKONDA
TSH_12 | verify the login functionality of valid user id and uppercase characters of password | Functional Testing | CHANDINI APPIKONDA
TSH_13 | verify the login funtionaltiy of invalid user id and invalid password | Functional Testing | CHANDINI APPIKONDA
TSH_14 | verify the login functionality of the invalid user id and valid password | Functional Testing | CHANDINI APPIKONDA
TSH_15 | verify the login functionality of the valid user id and valid password | Functional Testing | CHANDINI APPIKONDA
TSH_16 | verify the login funtionaltiy when a user enter lower case characters of user id and valid password | Functional Testing | CHANDINI APPIKONDA
TSH_17 | verify the login functionality of the valid user id and invalid password | Functional Testing | CHANDINI APPIKONDA
TSH_18 | verify the login functionality with special characters of user id and valid password | Functional Testing | CHANDINI APPIKONDA
TSH_19 | verify the login funtionaltiy of numeric user id and valid password | Functional Testing | CHANDINI APPIKONDA
User Story 3-Ajaykumar
TSH_20 | To Verify the Login functionality of Saucedemo, when user enter valid Username and invalid Password.wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_21 | To Verify the Login functionality of Saucedemo, when user enter invalid Username and valid Password.wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_22 | To verify the Login functionality of sucedemo, when user enter invalid username and invalid password. Wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_23 | To verify the Login functionality of sucedemo, when user enter valid username and valid password. Wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_24 | To Verify the Login functionality of Saucedemo, when user leaves Username field empty and valid Password.wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_25 | To Verify the Login functionality of Saucedemo, when user enter valid Username and leaves Password field empty.wheather login page working properly or not. | Functional Testing | AjayKumar
TSH_26 | To verify the functionality of Login button is clickable and accessible in Saucedemo application. | Functional Testing | AjayKumar
TSH_27 | To verify the user can view the list of available products in home page of Saucedemo application. | Usability Testing | AjayKumar
TSH_28 | To verify the user can add the product to the cart in home page of Saucedemo application. | Usability Testing | AjayKumar
TSH_29 | To verify the user can remove a product from the cart in home page of Saucedemo application. | Usability Testing | AjayKumar
TSH_30 | To verify the user can filter products by price in home page of Saucedemo application. | Usability Testing | AjayKumar
TSH_31 | To verify the user can complete the checkout process in cart information page of Saucedemo application. | Usability Testing | AjayKumar
TSH_32 | To verify the user can logout from the application. | Functional Testing | AjayKumar
User Story 4-Priyanka Aute
TSH_33 | To verify that the Checkout button is clickable or not | Functional Testing | Priyanka Aute
TSH_34 | To Verify that the Checkout functionality when the user enter correct First name, Last Name and ZipPostal Code | Functional Testing | Priyanka Aute
TSH_35 | To Verify that the Checkout functionality when the user enter Numeric data in First Name, Character data in Last Name and ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_36 | To Verify that the Checkout functionality when the user enter Numeric data in Last Name, Character data in First Name and ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_37 | To Verify that the Checkout functionality when the user enter character data in First Name, Last Name and ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_38 | To Verify that the Checkout functionality when the user enter Numeric data in First Name, Last Name and ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_39 | To Verify that the Checkout functionality when the user enter Numeric data in First Name and Last Name, Character data in ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_40 | To Verify that the Checkout functionality when the user do not enter any data in First Name, Last Name and ZipPostal Code. | Functional Testing | Priyanka Aute
TSH_41 | To Verify that the Cancel button of Checkout Page is visible and clickable. | Functional Testing | Priyanka Aute
TSH_42 | To Verify that the Finish button of Overview Page is visible and clickable. | Functional Testing | Priyanka Aute
User Story 5-Aruna
TSH_43 | To verify that a user can log in with valid credentials. | Functional Testing | Aruna
TSH_44 | To verify that a user cannot log in with invalid credentials. | Functional Testing,Negative Testing | Aruna
TSH_45 | To verify that an item can be added to the cart. | Functional Testing | Aruna
TSH_46 | To verify that an item can be removed from the cart and the cart icon shows the correct number of items | Functional Testing | Aruna
TSH_47 | To Verify that product details can be viewed. | Functional Testing | Aruna
TSH_48 | To Verify that products can be sorted by different criteria. | Functional Testing | Aruna
TSH_49 | To Verify that a user can complete the checkout process. | Functional Testing | Aruna
TSH_50 | To Verify that the correct message is displayed when the cart is empty. | Functional Testing,Negative Testing | Aruna
TSH_51 | To Verify that the website is responsive and works well on different screen sizes. | Usability Testing | Aruna
TSH_52 | To Verify that a user can log out successfully. | Functional Testing | Aruna
User Story 6-Kalle Bhavani
TSH_53 | To verify menu button accesibility after login | Functional Testing | Kalle Bhavani
TSH_54 | Verifying the menu options after clicking on it | Functional Testing | Kalle Bhavani
TSH_55 | Verifying the "About" button functionality in menu | Functional Testing | Kalle Bhavani
TSH_56 | Verifying "Logout" button functionality in menu | Functional Testing | Kalle Bhavani
TSH_57 | Verifying the close button functinality | Functional Testing | Kalle Bhavani
TSH_58 | Verify that "Add to cart" button is displayed or not | Functional Testing | Kalle Bhavani
TSH_59 | Verifying the functionality of clicking on the product for add to cart | Functional Testing | Kalle Bhavani
TSH_60 | Verifying that add to cart image shows count of items it contains | Functional Testing | Kalle Bhavani
TSH_61 | Verifying that added to cart products need to display after clicking on it | Functional Testing | Kalle Bhavani
TSH_62 | Verify that "Add to cart" button should changes to remove after adding to cart | Functional Testing | Kalle Bhavani
User Story 7-Aditi Kulkarni
TSH_63 | Verify that the User able to see the home page after click on login button by entering valid username and password. | Functional Testing | Aditi
TSH_64 | Verify that user see appropriate feedback when an incorrect password is entered during login. | Functional Testing | Aditi
TSH_65 | Verify that the Menu icon is displaying in all pages or not, click on it. Whether it is working properly or not. | Functional Testing | Aditi
TSH_66 | Verify that All Items option is working or not. Whether it is redirect to inventory page or not. | Functional Testing | Aditi
TSH_67 | Verify that About option is working or not. Whether it is redirect to saucelabs website or not. | Functional Testing | Aditi
TSH_68 | Verify that Checkout button is displaying on cart page or not. It is redirect to checkout-step-one page for the user information or not. | Functional Testing | Aditi
TSH_69 | Verify that form is available on checkout-step-one page or not. For gathering information of user to complete checkout process. | Functional Testing | Aditi
TSH_70 | Verify that the filter icon is present and clickable in the product page | Functional Testing | Aditi
TSH_71 | Verify that the products are displayed in alphabetical order from A to Z based on product name in the product page | Functional Testing | Aditi

## Test cases
TE Name | Test case ID | Test case name | Description | Test Steps | Test Data | Expected Result | Actual Result | Severity | Priority | Tested By | Test Status | Test Creation Date | Test Execution Date | DEFECT NO
Kristapadu Shamshannisha | TC_01 | Verify the visibility and accessibility of "add to cart" button on the product page. | To ensure the "Add to Cart" button is visible and accessible on the product page. | 1.Login to the sauce demo application. 2.Navigate to the product page. 3.Locate the "Add to Cart" button. 4.Check if the button is visible without scrolling. 5.Use a screen reader or keyboard navigation to verify accessibility. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | The "Add to Cart" button is clearly visible and located in the expected position on the product page. | The "Add to Cart" button is clearly visible and located in the expected position on the product page. | Medium | High | Kristapadu Shamshannisha | pass | 2024-06-14 | 2024-06-14
Kristapadu Shamshannisha | TC_02 | Verify that the "Add to Cart" button is clickable and adds items to the cart. | To ensure the "Add to Cart" button is clickable and successfully adds items to the cart. | 1.Login to the sauce demo application. 2.Navigate to the product page. 3.Click on the "Add to Cart" button. 4.Observe if the item is added to the cart. | Link:https://www.saucedemo.com/v1/index.html UserID :problem_user Password:secret_sauce | The "Add to Cart" button is clickable and the item is added to the cart . | Add to cart button adds items to my cart and it is clickabale. | High | High | Kristapadu Shamshannisha | fail | 2024-06-14 | 2024-06-14 | DEF_01
Kristapadu Shamshannisha | TC_03 | Verify that add to cart image shows count of items it contains. | To ensure the cart icon updates to show the count of items it contains. | 1.Login to the sauce demo application. 2.Add an item to the cart. 3.Check the cart icon for the updated item count. 4.Add another item and observe the change in item count. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | The cart icon accurately shows the count of items and the item count updates immediately upon adding items. | The item which is added is updated in cart and count is also indication is appeared. | Medium | Medium | Kristapadu Shamshannisha | pass | 2024-06-14 | 2024-06-14
Kristapadu Shamshannisha | TC_04 | Verify that items added to the cart opens product details page after clicking on the items in the cart | To ensure that clicking on items in the cart opens the product details page. |  | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | Clicking on the item in the cart navigates to the product details page and the product details page displays accurate information about the item. | By clicking on product item in cart page it navigates to product details page. | Medium | Medium | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
Kristapadu Shamshannisha | TC_05 | Verify that the "Add to Cart" button changes to remove button after adding item to cart. | To ensure the "Add to Cart" button changes to a "Remove" button after adding an item to the cart. | 1.Login to the sauce demo application. 2.Add an item to the cart. 3.Observe the "Add to Cart" button. 4.Verify if it changes to a "Remove" button. | 1.Login to the sauce demo application. 2.Add an item to the cart. 3.Click on the item in the cart. 4.Observe if the product details page is displayed. | The "Add to Cart" button changes to a "Remove" button and the "Remove" button is clearly labeled and functional. | Change of add to cart into remove button after adding product in cart. | Medium | High | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
Kristapadu Shamshannisha | TC_06 | Verify that items can be successfully removed from and re-added to the cart without errors. | To ensure items can be removed and re-added to the cart without errors. | 1.Login to the sauce demo application. 2.Add an item to the cart. 3.Remove the item using the "Remove" button. 4.Re-add the item to the cart. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | The item is successfully removed , can be re-added to the cart without errors and the cart count updates accurately. | Items previously added to the cart are removed and it can be readded to cart. | High | High | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
Kristapadu Shamshannisha | TC_07 | Verify that add to cart image is responsive and opens your cart page after clicking. | To ensure the cart icon is responsive and opens the cart page when clicked. | 1.Login to the sauce demo application. 2.Navigate to the product listing page. 3.Observe the cart icon on different devices and screen sizes. 4.Click on the cart icon. 5.Verify that the cart page opens. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | The cart icon is responsive and functional across different devicesand by clicking the cart icon navigates to the cart page. | Clicking cart icon navigates to cart page. | Medium | High | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
Kristapadu Shamshannisha | TC_08 | Verify that product details is displayed by clicking on the product image in home page. | To ensure that clicking on a product image on the product listing page displays the product details page. | 1.Login to the sauce demo application. 2.Navigate to the product listing page. 3.Click on a product image. 4.Observe if the product details page is displayed. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | Clicking on the product image navigates to the product details page and it shows comprehensive information about the product. | Product image in home page functions and navigate to product details page on clicking | Medium | Medium | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
Kristapadu Shamshannisha | TC_09 | Verify the back button in product details page returns to home page. | To ensure that the back button on the product details page returns to the home page. | 1.Login to the sauce demo application 2.Navigate to the product details page by clicking on a product image. 3.Locate and click the back button. 4.Observe if it navigates back to the home page. | Link:https://www.saucedemo.com/v1/index.html UserID : standard_user Password:secret_sauce | Clicking the back button navigates the user back to the home page. The home page retains the user's previous state (scroll position, filters). | back button in product details page navigates back to page where you left. | Medium | High | Kristapadu Shamshannisha | pass | 2024-06-15 | 2024-06-15
CHANDINI | TC_10 | to verify the login functionality with the valid user id and lower case characters of the password | To verify the behavior of login functionality of Saucedemo with valid user id and lower case characters of password to navigate to homepage | 1.open the Sauce demo application. 2.Enter t he valid id. 3.Enter the lower case characters of password. 4.click on login button. | Link--https://www.saucedemo.com/v1/ user id--standard_user password--asdfghjk | should land on homepage and see the results | A pop up box of an error message will be displayed | medium | medium | CHANDINI APPIKONDA | fail | 2024-06-15 | 2024-06-15 | DEF_02
CHANDINI | TC_11 | verify the login functionality of valid user id and special characters of password | to verify the behavior login functionality of Saucedemo valid user id and special characters of password to navigate to homepage | 1.open the Sauce demo application. 2.Enter t he valid id. 3.Enter the special characters of password. 4.click on login button. | Link--https://www.saucedemo.com/v1/ user id--standard_user password--!@#$%^&* | Error message displayed | A pop up box of an error message will be displayed | low | low | CHANDINI APPIKONDA | pass | 2024-06-15 | 2024-06-15
CHANIDNI | TC_12 | To verify the login functionality of valid user id and uppercase characters of password | To verify the behavior login functionality of saucedemo with valid user id and uppercase characters of password to navigate to homepage | 1.open the saucedemo application. 2.enter valid id. 3.enter the uppercase characters of the password 4.click on the login button | Link--https://www.saucedemo.com/v1/ user id--standard_user password--ASDFGHJKk | should land on homepage and see the results | A pop up box of an error message | medium | medium | CHANDINI APPIKONDA | fail | 2024-06-15 | 6700176 | DEF_03
CHANDINI | TC_13 | To verify the login funtionaltiy of invalid user id and invalid password | To verify the behavior login funtionaltiy of Saucedemo invalid user id and invalid password to navigate to homepage | 1.open the sausedemo application. 2.enter invalid id. 3.enter invalid password. 4.click on login button. | Link--https://www.saucedemo.com/v1/ user id--formal_user password--Adfgfdhc | Error message displayed | A pop up box of an error message will be displayed | high | high | CHANDINI APPIKONDA | Pass | 2024-06-15 | 2024-06-15
CHANDINI | TC_14 | TO verify the login functionality of the invalid user id and valid password | TO verify the behavior login functionality of the saucedemo with invalid user id and valid password to navigate to homepage | 1.open the sausedemo application. 2.enter invalid id. 3.enter valid password. 4.click on login button. | Link--https://www.saucedemo.com/v1/ user id--formal_user password--secret_sauce | Error message displayed | A pop up box of an error message will be displayed | high | high | CHANDINI APPIKONDA | Pass | 15 / 06 / 2024 | 15 / 06 / 2024
CHANDINI | TC_15 | To verify the login functionality of the valid user id and valid password | To verify the behaviour of login functionality of the Saucedemo wiht valid user id and valid password to navigate the homepage | 1.open the sausedemo application. 2.enter the valid id. 3.enter the valid password. 4.click on login button | link--https://www.saucedemo.com/v1/ user id--standard_user password--secret_sauce | user should land on home page | navigated to the homepage | high | high | CHANDINI APPIKONDA | Pass | 2024-06-15 | 15 / 06 /2024
CHANDINI | TC_16 | TO verify the login funtionaltiy when a user enter lower case characters of user id and valid password | TO verify the behaviour of login funtionaltiy when a user enter lower case characters of user id and valid password to navigate to homepage | 1.open the sausedemo application. 2.enter the lower case characters of id. 3.enter the valid password. 4.click on login button | link--https://www.saucedemo.com/v1/ user id--asdfghjjk password--secret_sauce | Error message displayed | A pop up box of an error message will be displayed | medium | high | CHANDINI APPIKONDA | pass | 2024-06-15 | 15 / 06 / 2024
CHANDINI | TC_17 | To verify the login functionality when a user enters valid id and invalid passwrod | To verify the behaviour of the login functionality when a suer enters the valid user id and valid apssword | 1.open the saucedemo application 2.enter valid user id 3.enter invalid password 4.click on login button | link--https://www.saucedemo.com/v1/ user id--standard_user password--no_sauce | Error message displayed | A pop up box of an error message will be displayed | low | high | CHANDINI APPIKONDA | pass | 15 / 06 /2024 | 15 / 06 2024
CHANDINI | TC_18 | To verify the login functionality with special characters of user id and valid password | To verify the behaviour of login functionality with saucedemo with special characters of user id and valid password to navigate to homepage | 1.open the saucedemo application 2.enter invalid user id 3.enter valid password 4.click on login button | link--https://www.saucedemo.com/v1/ user id--!@#$%^&* password--secret_sauce | Error message displayed | A pop up box of an error message will be displayed | low | low | CHANDINI APPIKONDA | pass | 15 / 06 / 2024 | 15 / 06 /2024
CHANIDNI | TC_19 | To verify the login funtionaltiy of numerics user id and valid password | to verify the behaviour login funtionaltiy of numerics user id and validpassword to navigate to homepage | 1.open the saucedemo application 2.enter numerics user id 3.enter valid password 4.click on login button | link--https://www.saucedemo.com/v1/ user id--123456789 password--secret_sauce | error message displayed | A pop up box of an error message will be displayed | high | medium | CHANDINI APPIKONDA | pass | 15 / 06 / 2024 | 15 / 06 /2024
AjayKumar | TC_20 | Verify the login functionality of saucedemo when a valid username and invalid password | Verify the behavior of the login functionality when a user enter wrong username and correct password | 1.Open the saucedemo application 2. Enter a invalid username 3.Enter valid password. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Standard Password:secret_sauce | Error message | A pop up box of an error message is Epic sadface: Username and password do not match any user in this service | High | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15 | DEF_04
AjayKumar | TC_21 | Verify the login functionality of Saucedemo with invalid Username and valid password. | Verify the behavior of the login functionality when a user enter correct Username and wrong password | 1.open the saucedemo application 2. Enter a valid Username 3.Enter invalid password. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Standard _user Password:secret | Error message | A pop up box of an error message is Epic sadface: Username and password do not match any user in this service | High | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15 | DEF_05
AjayKumar | TC_22 | Verify the login functionality of Saucedemo with invalid Username and invalid password. | Verify the behaviour of the login functionality when user cannot login invalid credentials. | 1.open the saucedemo application 2. Enter a invalid Username 3.Enter invalid password. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Standard Password:secret | Error message | A pop up box of an error message is Epic sadface: Username and password do not match any user in this service | High | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15 | DEF_06
AjayKumar | TC_23 | Verify the login functionality of Saucedemo with valid Username and valid password. | Verify the behaviour of the login functionality when user can login valid credentials. | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Standard _user Password:secret_sauce | User should land on home page | User should landed on the home page and to see the products. | Medium | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_24 | Verify the login functionality of Saucedemo with Username is empty and valid password. | Verify the behavior of the login functionality when a user leave the username field empty and valid password | 1.open the saucedemo application 2.Leave the Username field empty. 3.Enter valid password. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Password:secret_sauce | Error message | A pop up box of an error message is Epic sadface: Username is Required. | Medium | High | AjayKumar | Pass | 2025-06-15 | 2026-06-15 | DEF_07
AjayKumar | TC_25 | Verify the login functionality of Saucedemo with valid username and empty password. | Verify the behavior of the login functionality when a user enter valid Username and leave the password field empty. | 1.open the saucedemo application 2.Enter a valid Username 3.Leave the password field empty. 4.Click on login button. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password: | Error message | A pop up box of an error message is Epic sadface: Password is Required. | Medium | High | AjayKumar | Pass | 2026-06-15 | 2027-06-15 | DEF_08
AjayKumar | TC_26 | Verify the Login Button Accessibility. | Verify that the login button is clickable and accessible. | 1.open the saucedemo application 2. Enter a valid Username 3.Enter valid password. 4.Check if the login button is clickable. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | The login button should be clickable and should function as expected. | User should click on login button and landed on the home page and to see the products. | Low | Medium | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_27 | Verify the Home page functionality of Saucedemo as View Product Catalog. | verify that the user can view the list of avaliable products. | 1. Login to the Saucedemo application. 2. Observe the product catalog on the dashboard. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | A product should be display each with an image, name, price, and Description. | A product should be displayed each with an image, name, price, and Description. | Medium | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_28 | Verify the Home page functionality of Saucedemo as Product Add to Cart. | Verify that the user can add a product to the cart. | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce Product: Any available product | The product should be added to the cart. | The product should be added to the cart, and the cart icon should display the updated number of items. | Medium | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_29 | Verify the Home page functionality of Saucedemo as Remove product from cart. | Verify that the user can remove a product from the cart. | 1. Login to the Saucedemo application. 2.Click on the "Add to Cart" button for a product. 3. Click on the cart icon. 4. Click the "Remove" button next to the product. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce Product: Any available product added to the cart | The product should be Remove from the cart. | The product should be Remove from the cart and the cart icon should update accordingly. | Medium | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_30 | Verify the Home page functionality of Saucedemo as Filter Product by Price. | Verify that the user can filter products by price. | 1. Login to the Saucedemo application. 2.Click on the filter dropdown. 3. Select "Price(low to high)". | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | Product should be sorted by price from low to high. | Product should be sorted by price from low to high. | Low | Medium | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_31 | Verify the cart functionality of Saucedemo as Checkout Process. | Verify that the user can complete the checkout process. | 1. Login to the Saucedemo application. 2. Add one or more products to the cart. 3. Click on the Cart icon. 4. click The "Checkout" Button. 5. Enter Firsrt Name, Last Name, Postalcode. 6. Click on the Continue Button. 7. Click on the Finish Button. 8. confirm the order. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce Checkout information: Valid First Name, LastName, Postal code. | The user should be able to complete the checkout process. | The user should be able to complete the checkout process and receive an order conformation. | High | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
AjayKumar | TC_32 | Verify the Logout Functionality of Saucedemo. | Verify that the user can log out from the application. | 1. Login to the Saucedemo application. 2. Click on the menu button. 3. Click the "Logout" button. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | The user should be logout and redirect to the login page. | The user should be logged out and redirected to the login page. | Medium | High | AjayKumar | Pass | 2024-06-15 | 2024-06-15
Priyanka Aute | TC_33 | Verify the checkout button is visible and clickable. | To ensure that the "CheckOut" button is vissible and clickable or not. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce | The Checkout button should be clickable and it should redirect user to the User Information Page | The Checkout button is clickable and it redirect the user to CheckOut Page | Medium | High | Priyanka Aute | Pass | 2024-06-16 | 2024-06-16
Priyanka Aute | TC_34 | Verify the Checkout functionality when the user enter correct First name, Last Name and ZipPostal Code. | To verify that when the user enters correct First Name, Last Name, and ZipPost Code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Valid First name, Last name, ZipPostal Code | The User should be redirected to the Overview page. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Pass | 2024-06-16 | 2024-06-16
Priyanka Aute | TC_35 | Verify the Checkout functionality when the user enter Numeric in First Name, Characters in Last Name and ZipPostal Code. | To verify that when the user enters Numeric in First Name, Characters in Last Name and ZipPostal Code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Numeric data in First name, Characters data in Last name and ZipPostal Code | The Popup box of error message should be displayed. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Fail | 2024-06-16 | 2024-06-16 | DEF_09
Priyanka Aute | TC_36 | Verify the Checkout functionality when the user enter Numeric in Last Name, Characters in First Name and ZipPostal Code. | To verify that when the user enters Numeric in Last Name , Characters in First Name and Zippostal Code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Numeric data in Last name, Characters data in First name and ZipPostal Code | The Popup box of error message should be displayed. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Fail | 2024-06-16 | 2024-06-16 | DEF_10
Priyanka Aute | TC_37 | Verify the Checkout Functionality when the user enter Characters in First name, last name and Zippostal code. | To verify that when the user enters Characters data in first name, last name and zippostal code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Characters data in First name, last name and ZipPostal Code | The Popup box of error message should be displayed. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Fail | 2024-06-16 | 2024-06-16 | DEF_11
Priyanka Aute | TC_38 | Verify the Checkout Functionality when the user enter Numeric data in First name, last name and Zippostal code. | To verify that when the user enters Numeric data in first name, last name and zippostal code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Numeric data in First name, last name and ZipPostal Code | The Popup box of error message should be displayed. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Fail | 2024-06-16 | 2024-06-16 | DEF_12
Priyanka Aute | TC_39 | Verify the Checkout Functionality when the user enter Numeric data in First name and last name , character data in Zippostal code. | To verify that when the user enters Numeric data in first name and last name, Character data in zippostal code. | 1. Login to the Saucedemo application. 2. Click on the Cart button. 3. Click on the Checkout button. 4. Enter First Name, Last Name, ZipPostal Code 5. Click on the Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: Numeric data in First name, last name and character data in ZipPostal Code | The Popup box of error message should be displayed. | The User is redirected to the Overview Page. | Medium | High | Priyanka Aute | Fail | 2024-06-16 | 2024-06-16 | DEF_13
Priyanka Aute | TC_40 | Verify the Checkout Functionality when the user do not enter First name, last name and Zippostal code. | To verify that when the user do not enter any data in the first name, last name and zippostal code. | 1. Login to the Saucedemo application. 2. Click on th Cart Button. 3. Click on the Checkout button. 4. Click on Continue button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout information: No data | The Popup box of error message should be displayed. | The Popup box of error message is displayed. | Medium | High | Priyanka Aute | Pass | 2024-06-16 | 2024-06-16
Priyanka Aute | TC_41 | Verify the Cancel button of the Checkout page is visible and clickable. | To Verify that the Cancel button of Checkout page is visible and clickable. | 1. Login to the Saucedemo application. 2. Click on th Cart Button. 3. Click on the Checkout button. 4. Click on Cancle button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce | The User should be redirected to the Cart page. | The User is redirected to the cart page. | Medium | High | Priyanka Aute | Pass | 2024-06-16 | 2024-06-16
Priyanka Aute | TC_42 | Verify the "Finish" button of Overview Page is visible and clickable. | To verify that the "Finish" button of Overview page is visibal and clickable. | 1. Login to the Saucedemo application. 2. Click on th Cart Button. 3. Click on the Checkout button. 4. Click on Continue button. 5. Click on Finish button. | Link-- https://www.saucedemo.com/v1/ Username: standard_user Password: secret_sauce Checkout Information: Valid First name, Last Name, ZipPostal Code | The user should be able to see the Thank You Message | The user is able to see the Thank You Message. | Medium | High | Priyanka Aute | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_43 | verify the login functionality with valid details | To verify that a user can log in with valid credentials. | 1.Navigate to the SwagLabs SauceDemo login page. 2.Enter valid username and password. 3.Click the login button. 4.Verify that the user is redirected to the inventory page. | Link--https://www.saucedemo.com/v1/ Username: Standard_user or Username: locked_out_user or Username:problem_user or Username:performance_glitch_user Password:secret_sauce | User is successfully logged in and navigated to the inventory page | User is successfully logged in and navigated to the inventory page | High | High | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_44 | verify the login functionality with invalid details | To verify that a user cannot log in with invalid credentials. | 1.Navigate to the SwagLabs SauceDemo login page. 2.Enter invalid username and/or password. 3.Click the login button. 4.Verify that an error message is displayed. | Username: "invalid_user" Password: "invalid_password" | Error message indicating incorrect username or password is displayed. | An Error message "Epic sadface: Username and password do not match any user in this service" should be displayed | Medium | Medium | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_45 | verify the add item to cart functionality | To verify that an item can be added to the cart. | 1.Log in with valid credentials. 2.Navigate to the inventory page. 3.Click the "Add to cart" button for a product. 4.Verify that the cart icon shows the correct number of items (1). | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce Product to add to cart (e.g., Sauce Labs Backpack) | Item is successfully added to the cart, and the cart icon shows the correct number of items. | Sauce Labs Backpack is successfully added to the cart, and the cart icon shows the correct number of items as 1. | High | High | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_46 | verify the remove item from cart functionality | To verify that an item can be removed from the cart and the cart icon shows the correct number of items | 1.Log in with valid credentials and add an item to the cart. 2.Navigate to the cart page. 3.Click the "Remove" button for the product in the cart. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | Item is successfully removed from the cart. | Items removed from the cart but still the carti icon shows the number of items | High | High | Aruna | Fail | 2024-06-16 | 2024-06-16 | Dt_01
Aruna | TC_47 | verify the product details | To Verify that product details can be viewed. | 1.Log in with valid credentials. 2.Navigate to the inventory page. 3.Click on a product title. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | Product details page is displayed with correct information (price, description, image). | The product Sauce Labs Bike Light's price,description and image should be displayed with correct information | Medium | Medium | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_48 | verify the products can be sorted based on selected option | To Verify that products can be sorted by different criteria. | 1.Log in with valid credentials. 2.Navigate to the inventory page. 3.Select a sort option from the dropdown menu (e.g., "Price (low to high)"). | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | Products are sorted correctly based on the selected option. | products are sorted by Name(A-Z), NAme(Z-A), Price(Low-High), Price(High-Low) based on the selected option. | Medium | Medium | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_49 | verify the checkout process | To Verify that a user can complete the checkout process. | 1.Log in with valid credentials and add items to the cart. 2.Navigate to the cart page. 3.Click the "Checkout" button. 4.Enter valid checkout information (First Name: Aruna, Last Name: Anu, Postal Code: 12345). 5.Click the "Continue" button. 6.Click the "Finish" button. | FirstName: Aruna, Last NAme: Anu, Postal Code: 12345 | Order is successfully placed and confirmation page is displayed. | Order is successfully placed and confirmation page is displayed with dispatch details | High | High | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_50 | verify the empty cart message | To Verify that the correct message is displayed when the cart is empty. | 1.Log in with valid credentials. 2.Navigate to the cart page. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | Correct message indicating the cart is empty should be displayed | Message indicating the cart is empty is not displayed | Medium | Medium | Aruna | Fail | 2024-06-16 | 2024-06-16 | Dt_02
Aruna | TC_51 | verify the responsive design of the sauce demo | To Verify that the website is responsive and works well on different screen sizes. | 1.Open the website on different devices (e.g., desktop, tablet, mobile). | Link--https://www.saucedemo.com/v1/ | The website layout adjusts appropriately and functionality is maintained across different screen sizes. | The website layout adjusts appropriately and functionality is maintained across different screen sizes for laptop,mobile and desktop | Medium | Medium | Aruna | Pass | 2024-06-16 | 2024-06-16
Aruna | TC_52 | Verify the Logout Functionality of Saucedemo. | To Verify that a user can log out successfully. | Log in with valid credentials. Click on the menu button. Click the logout button. Verify that the user is redirected to the login page. | Link--https://www.saucedemo.com/v1/ Username: Standard_user Password:secret_sauce | User is successfully logged out and redirected to the login page. | User is successfully logged out after clicking logout button and redirected to the login page. | Medium | Medium | Aruna | Pass | 2004-06-16 | 2004-06-16
Kalle Bhavni | TC_53 | To verify menu button is clickable or not | verify that clicking on menu button opens the menu | 1. Login to saucedemo website 2. Enter valid user name and password 3. Click on login 4. Click on menu button | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The menu button should be visible on the main page and clickable | The menu button had succesully visibled on the main page and clickable | Medium | High | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16
Kalle Bhavni | TC_54 | To verify options in menu button displays or not | verify that all the options are displayed when the button is clicked | 1.Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Click on the menu button 5. Observe all options displayed in the menu | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The options in the menu should be displayed when clicking on the menu button | The menu button successfully displays options are All Items,About,Logout and Reset app state when clicking on menu button | High | Medium | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16
Kalle Bhavni | TC_55 | Verifying that clicking on "About" redirecting to about us page or not | verify that by selecting "About" from the menu navigates to the about us page | 1.Login to the Sauce demo application 2. Enter valid user name and password 3. Click on login 4. Click on the menu button 5. Click on "About" | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The user should navigated to about us page of sauce demo application | The user had succesfuly navigated to the about us page of sauce demo application | mdium | mdium | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16
Kalle Bhavni | TC_56 | verifying the logout functionality of application by clicking on "Logout" from the menu which logout's the user | verify that by selecting "Logout" from menu the user should logout from application | 1.Login to the Sauce demo application 2. Enter valid user name and password 3. Click on login 4. Click on the menu button 5. Click on "Logout" | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The user should logout from application when clicking on "Logout" in the menu | The user had failed to logout from the application by clicking on the "Logout" from the menu | High | High | Kalle Bhavni | Fail | 2024-06-16 | 2024-06-16 | DEF_16
Kalle Bhavni | TC_57 | Verifying the close button functionality to close the options | verify that re-clicking the menu button which closes the menu | 1. Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Click on menu button to open the menu 5. Click outside the menu or re-click the menu button | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The menu should be closed | The menu is successfuly closed and displays home page | Medium | High | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16
Kalle Bhavni | TC_58 | verifying that "Add to cart" button is clickable or not | Verify that add to cart button is displayed and clickable | 1. Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Navigate to the product page 5. Locate the "Add to Cart" button 6. Click on "Add to cart" | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The "Add to Cart" button should be clickable | The "Add to Cart" button is clickable | High | Medium | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16
Kalle Bhavni | TC_59 | Verifying the functinality of "Add to cart" by adding items to cart | verify that the cart button is visible and accesible on the product page | 1. Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Navigate to the product page 5. Locate the "Add to Cart" button 6. Click on "Add to cart" 7. Observe if the item is added to cart | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The item should added to cart | The item is failed to add in the cart | High | Fail | Kalle Bhavni | Pass | 2024-06-16 | 2024-06-16 | DEF_17
Kalle Bhavni | TC_60 | Verifying that add to cart image shows count of items it contains | verify that cart icon updates to show the count of items it contains | 1. Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Add an item to the cart 5. Check the cart icon for the updated item count 6. Add another item and observe the change in item count | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The cart icon should show the count of items and the item count updates immediately upon whenever we adding them | The item which is added is updated in cart and count is also indication is appeared successfully | Medium | Low | Kalle Bhavni | Pass | 2024-06-17 | 2024-06-17
Kalle Bhavni | TC-61 | Verifying that items added to the cart opens product details page after clicking on the items in the cart | verify that clicking on items in the cart opens the product details page | 1. Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Add an item to the cart 5. Check the cart icon for the updated item count 6. Observe for the product details which is added | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | Clicking on the item in the cart navigates to the product details page and the product details page displays accurate information about the item. | By clicking on product item in cart it successfuly navigates to product details page | Medium | Low | Kalle Bhavni | Pass | 2024-06-17 | 2024-06-17
Kalle Bhavni | TC-62 | Verifying that the "Add to Cart" button changes to remove button after adding item to cart | Verify that add to cart button changes to remove button after adding an item to cart | 1.Login to the sauce demo application 2. Enter valid user name and password 3. Click on login 4. Add an item to the cart 5. Click on the item in the cart 6. Observe if the product details page is displayed. | 1. Enter the URL of the saucedemo websites: https://www.saucedemo.com/v1/ 2. User name: locked_out_user Password: secret_sauce | The "Add to Cart" button should changes to "Remove" button and the "Remove" button is clearly visible and work | The Add to cart button is successfuly changed to remove button and the reomove button is clearly visible and functioning | Medium | Low | Kalle Bhavni | Pass | 2024-06-17 | 2024-06-17
Aditi | TC_63 | Verify the login functionality when a user enter valid username and valid password. | This test verifies that users can successfully log in when they enter a valid username and password combination. | 1.Open the saucedemo application 2.Enter a valid username (e.g., standard_user) and a valid password (e.g., secret_sauce). 3.Click on the login button. 4.Verify that the user is logged in successfully and redirected to the main page of Swag Labs | URL : https://www.saucedemo.com username:standard_user Password:secret_sauce | User should be successfully logged in and redirected to the main page. | User logged in Successfully | Medium | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_64 | Verify the login functionality when a user enter valid username and invalid password. | This test ensures that users cannot log in with an invalid password even when the username is valid | 1.Open the saucedemo application 2.Enter a valid username (e.g., standard_user) and an invalid password. 3.Click on the login button. 4.Verify that the login fails with an appropriate error message indicating that the username and password do not match. | URL : https://www.saucedemo.com Username : standard_user Password:Incorrect_password | Login should fail with an appropriate error message indicating incorrect password. | Login failed and error message is displayed | Medium | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_65 | Verify the Menu icon functionality. | Verify the behaviour of Menu icon on all pages when user click on it. | 1. Open the browser and enter the URL. Then click Enter. 2. Login with given test data. 3. Navigate to Menu icon top-left on all pages. 4.Click on Menu icon. | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | The Menu icon should be clickable and show different options. | The menu icon is showing different options like All Items, About, Logout and Reset App State. | High | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_66 | Verify that "All Items" is clickable in Menu. | Verify the behaviour of All Items option in menu on all pages when user click on it. | 1. Open the browser and enter the URL. Then click Enter. 2. Login with given test data. 3. Navigate to Menu icon top-left on all pages. 4. Click on Menu icon then select All Items option. | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | All Items option should be redirect to inventory page. | All Items option is able to redirect to inventory page. | Medium | Medium | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_67 | Verify that "About" is clickable in Menu. | Verify the behaviour of About option in menu on all pages when user click on it. | 1. Open the browser and enter the URL. Then click Enter. 2. Login with given test data. 3. Navigate to Menu icon top-left on all pages. 4. Click on Menu icon then select About option. | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | About option should be redirect to saucelabs website. | About option is redirect to saucelabs landing page. | Medium | Medium | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_68 | Checkout Button Visibility | Verify the "Checkout" option is displayed and clickable on the cart page. | 1. Verify the form is displayed on checkout-step-one page. 2. Try to proceed with a blank form and ensure it is not allowed. 3. Try to proceed with blank fields and ensure it is not allowed. | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | "Checkout" option should be displayed and clickable. Redirect to checkout-step-one page. | "Checkout" button is visible and redirects to checkout-step-one page. | High | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_69 | Verify User Details Form | Verify that checkout-step-one page has a form for user detail. | 1. Verify the form is displayed on checkout-step-one page. 2. Try to proceed with a blank form and ensure it is not allowed. 3. Try to proceed with blank fields and ensure it is not allowed. | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | The form should be displayed. | Form is displayed and prevents continuation with empty fields. | High | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_70 | Verify that the filter icon is present and clickable in the product page | The filter icon should be present and clickable on the top right corner of the product page | 1. Open the browser and enter the URL and click enter button. 2. The user should be redirected to the login page of the SauceDemo website. 3. Log in with valid credentials(username, password). 4. After successful login, Click on the filter icon present in the top right corner of the product page 5. The filter icon should display the drop-down options such as Name(A to Z), Name(Z to A), Price(low to high), price(high to low) | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | The filter icon should be present and clickable on the top right corner of the product page | The filter icon is present and clickable on the right corner of the product page | High | High | Aditi | Pass | 6/16/2024 | 6/16/2024
Aditi | TC_71 | Verify that the products are displayed in alphabetical order from A to Z based on product name in the product page | The products should be displayed in alphabetical order from A to Z based on product name in the product page when the Name(A to Z) option is clicked in the filter drop-down options | 1. Open the browser and enter the URL and click enter button. 2. The user should be redirected to the login page of the SauceDemo website. 3. Log in with valid credentials(username, password). 4. After successful login, Click on the filter icon present in the top right corner of the product page 5. Click on the Name(A to Z) from the drop-down option of the filter icon. The products should be displayed based on the alphabetical order of the product names | URL : https://www.saucedemo.com username : standard_user password : secret_sauce | the products are displayed in alphabetical order from A to Z based on product name in the product page | the products are displayed in alphabetical order from A to Z based on product name in the product page | High | High | Aditi | Pass | 6/16/2024 | 6/16/2024

## Defects
TE Name | Defect number | Project Name | Module Name | Requirement Number | Test Case ID | Summary | Description | Issues | Severity | Priority | Assign to | Screen Shots
Kristapadu Shamshannisha | DEF_01 | Saucedemo | Add To Cart button | REQ_01 | TC_02 | The add to cart button is not clickable while logged in as problem_user | To ensure the "Add to Cart" button is clickable and successfully adds items to the cart. | application is loading with problem_user credential. | High | High | Shamshannisha
CHANDINI | DEF_02 | Saucedemo | click on login button | REQ_02 | TC_10 | click on login button | verify the behaviour of the login functionality when a user enters the valid user id and lower cases characters of the password | Click on login button don't opening to the homepage | medium | medium | CHANDINI APPIKONDA
CHANDINI | DEF_03 | Saucedemo | click on login button | REQ_03 | TC_12 | click on login button | verify the behaviour of the login functionality when a user enters the valid user id and upper cases characters of the password | Click on login button don't opening to the homepage | medium | medium | CHANDINI APPIKONDA
AjayKumar | DEF_04 | Saucedemo | Login ID Username | REQ_04 | TC_20 | Click on Login Button functionality | Verify the login functionality of saucedemo when a valid username and invalid password | Didn't access home page while click on login button | Medium | High | Ajaykumar
AjayKumar | DEF_05 | Saucedemo | Password | REQ_05 | TC_21 | Click on Login Button functionality | Verify the login functionality of Saucedemo with invalid Username and valid password. | Didn't access home page while click on login button | Medium | High | Ajaykumar
AjayKumar | DEF_06 | Saucedemo | LoginID password | REQ_06 | TC_22 | Click on Login Button functionality | Verify the login functionality of Saucedemo with invalid Username and invalid password. | Didn't access home page while click on login button | Medium | High | Ajaykumar
AjayKumar | DEF_07 | Saucedemo | Login ID Username field empty | REQ_07 | TC_24 | Click on Login Button functionality | Verify the login functionality of Saucedemo with Username is empty and valid password. | Didn't access home page while click on login button | Medium | High | Ajaykumar
AjayKumar | DEF_08 | Saucedemo | Password field empty | REQ_08 | TC_25 | Click on Login Button functionality | Verify the login functionality of Saucedemo with valid username and empty password. | Didn't access home page while click on login button | Medium | High | Ajaykumar
Priyanka Aute | DEF_09 | Saucedemo | Validation of CheckOut fields | REQ_09 | TC_35 | Validating the Checkout fields First Name, Last Name, Zippostal Code. | Verify the Checkout functionality when the user enter Numeric in First Name, Characters in Last Name and ZipPostal Code. | Didn't show the Popup error message for invalid First Name and Zippostal Code. | Medium | High | Priyanka Aute
Priyanka Aute | DEF_10 | Saucedemo | Validation of CheckOut fields | REQ_10 | TC_36 | Validating the Checkout fields First Name, Last Name, Zippostal Code. | Verify the Checkout functionality when the user enter Numeric in Last Name, Characters in First Name and ZipPostal Code. | Didn't show the Popup error message for invalid Last Name and Zippostal Code. | Medium | High | Priyanka Aute
Priyanka Aute | DEF_11 | Saucedemo | Validation of CheckOut fields | REQ_11 | TC_37 | Validating the Checkout fields First Name, Last Name, Zippostal Code. | Verify the Checkout Functionality when the user enter Characters in First name, last name and Zippostal code. | Didn't show the Popup error message for invalid Zippostal Code. | Medium | High | Priyanka Aute
Priyanka Aute | DEF_12 | Saucedemo | Validation of CheckOut fields | REQ_12 | TC_38 | Validating the Checkout fields First Name, Last Name, Zippostal Code. | Verify the Checkout Functionality when the user enter Numeric data in First name, last name and Zippostal code. | Didn'd show the Popup error message for invalid First Name and Last Name. | Medium | High | Priyanka Aute
Priyanka Aute | DEF_13 | Saucedemo | Validation of CheckOut fields | REQ_13 | TC_39 | Validating the Checkout fields First Name, Last Name, Zippostal Code. | Verify the Checkout Functionality when the user enter Numeric data in First name and last name , character data in Zippostal code. | Didn't show the Popup error message for invalid First Name, Last Name and Zippostal Code. | Medium | High | Priyanka Aute
Aruna | DEF_14 | Saucedemo | Remove item from cart | REQ_14 | TC_46 | Remove items from the cart and check the cart icon for number of items are reduced | To verify that an item can be removed from the cart and the cart icon shows the correct number of items | Items are succesfully remove but still the number of items on the cart icon remains same | HIgh | High | Aruna
Aruna | DEF_15 | Saucedemo | Empty cart verification | REQ_15 | TC_50 | Verify the empty cart message | To Verify that the correct message is displayed when the cart is empty. | Message indicating the cart is empty is not displayed | Medium | Medium | Aruna
Kalle Bhavni | DEF_16 | Saucedemo | Click on logout button | REQ_16 | TC_56 | Logout button is not clickable in the options of menu | Verify that by selecting Logout from menu the user should logout from aplication | the application is not responding even after clicling on logout option | High | High | Kalle Bhavani
Kalle Bhavni | DEF_17 | Saucedemo | Add To Cart button functionality | REQ_17 | TC_59 | Item failed to add | verify that the cart button is visible and accesible on the product page | The application failed to add product in to the cart | High | High | Kalle Bhavani
Aditi | DEF_18 | Saucedemo | Checkout module. | REQ_18 | TC_70 | Click on 'Continue' button in 'Checkout' option with space as input in input fields. | Verify the behaviour of the website after the user clicked on 'Continue' button in 'Checkout' option with space as inputs in input fields. | The input fields take even space as input. | Medium | High | Aditi

## Defect_Snapshots
Defect ID | Test Case ID | Failed Screenshots
DEF_01 | TC_02
DEF_02 | TC_10
DEF_03 | TC_12
DEF_04 | TC_20
DEF_05 | TC_21
DEF_06 | TC_22
DEF_07 | TC_24
DEF_08 | TC_25
DEF_09 | TC_35
DEF_10 | TC_36
DEF_11 | TC_37
DEF_12 | TC_38
DEF_13 | TC_39
DEF_14 | TC_46
DEF_15 | TC_50
DEF_16 | TC_56
DEF_17 | TC_59
DEF_18 | TC_70

## Test excution details
Test Case ID | Test Case Name | Screenshots | TestCase Execution Date | TestCase Execution Start Time | TestCase Execution END Time
TC_01 | Verify the visibility and accessibility of "add to cart" button on the product page. |  | 2024-06-15 | 21:00 | 21:09
TC_02 | Verify that the "Add to Cart" button is clickable and adds items to the cart. |  | 2024-06-15 | 21:10 | 21:13
TC_03 | Verify that add to cart image shows count of items it contains. |  | 2024-06-15 | 21:15 | 21:18
TC_04 | Verify that items added to the cart opens product details page after clicking on the items in the cart. |  | 2024-06-15 | 21:20 | 21:25
TC_05 | Verify that the "Add to Cart" button changes to remove button after adding item to cart. |  | 2024-06-15 | 21:27 | 21:31
TC_06 | Verify that items can be successfully removed from and re-added to the cart without errors. |  | 2024-06-15 | 21:35 | 21:37
TC_07 | Verify that add to cart image is responsive and opens your cart page after clicking. |  | 2024-06-15 | 21:40 | 21:44
TC_08 | Verify that product details is displayed by clicking on the product image in home page. |  | 2024-06-15 | 21:45 | 21:46
TC_09 | Verify the back button in product details page returns to home page. |  | 2024-06-15 | 21:50 | 21:53
TC_10 | To verify the login functionality of valid user id and lower case characters of password |  | 15 / 06 /2024 | 15:00 pm | 15:03 pm
TC_11 | verify the login functionality of valid user id and special characters of password |  | 15 / 06 / 2024 | 15:07 pm | 15:12 pm
TC_12 | To verify the behavior login functionality of saucedemo with valid user id and uppercase characters of password to navigate to homepage |  | 15 / 06 /2024 | 15:07 pm | 15:11 pm
TC_13 | To verify the login funtionaltiy of invalid user id and invalid password |  | 15 / 06 / 2024 | 15:15 pm | 15:20 pm
TC_14 | TO verify the login functionality of the invalid user id and valid password |  | 15 / 06 /2024 | 15:21 pm | 15:24 pm
TC_15 | To verify the login functionality of the valid user id and valid password |  | 15 / 06 / 2024 | 15:30 pm | 15:34 pm
TC_16 | verify the login funtionaltiy when a user enter lower case characters of user id and valid password |  | 15 / 06 / 2024 | 15:40 pm | 15:43 pm
TC_17 | to verify the login functionality of the valid user id and invalid password |  | 15 / 06 /2024 | 16:02 pm | 16:05 pm
TC_18 | To verify the login functionality with special characters of user id and valid password |  | 15 / 06 /2024 | 16:11 pm | 16:15 pm
TC_19 | To verify the login funtionaltiy of numeric id and valid password |  | 15 / 06 / 2024 | 16:22 pm | 16:25 pm
TC_20 | Verify the login functionality of saucedemo when a valid username and invalid password. |  | 2024-06-15 | 10:03 AM | 10:05 AM
TC_21 | Verify the login functionality of Saucedemo with invalid Username and valid password. |  | 2024-06-15 | 10:07 AM | 10:09 AM
TC_22 | Verify the login functionality of Saucedemo with invalid Username and invalid password. |  | 2024-06-15 | 10:12 AM | 10:15 AM
TC_23 | Verify the login functionality of Saucedemo with valid Username and valid password. |  | 2024-06-15 | 10:17 AM | 10:19 AM
TC_24 | Verify the login functionality of Saucedemo with Username is empty and valid password. |  | 2024-06-15 | 10:22 AM | 10:25 AM
TC_25 | Verify the login functionality of Saucedemo with valid username and empty password. |  | 2024-06-15 | 10:29 AM | 10:33 AM
TC_26 | Verify the Login Button Accessibility. |  | 2024-06-15 | 10:35 AM | 10:37 AM
TC_27 | Verify the Home page functionality of Saucedemo as View Product Catalog. |  | 2024-06-15 | 10:40 AM | 10:43 AM
TC_28 | Verify the Home page functionality of Saucedemo as Product Add to Cart. |  | 2024-06-15 | 10:45 AM | 10:48 AM
TC_29 | Verify the Home page functionality of Saucedemo as Remove product from cart. |  | 2024-06-15 | 10:52 AM | 10:55 AM
TC_30 | Verify the Home page functionality of Saucedemo as Filter Product by Price. |  | 2024-06-15 | 14:02 PM | 14:06 PM
TC_31 | Verify the cart functionality of Saucedemo as Checkout Process. |  | 2024-06-15 | 14:09 PM | 14:12 PM
TC_32 | Verify the Logout Functionality of Saucedemo. |  | 2024-06-15 | 14:15 PM | 14:17 PM
TC_33 | Verify the checkout button is visible and clickable. |  | 2024-06-16 | 9:05 | 9:20
TC_34 | Verify the Checkout functionality when the user enter correct First name, Last Name and ZipPostal Code. |  | 2024-06-16 | 10:00 | 10:20
TC_35 | Verify the Checkout functionality when the user enter Numeric in First Name, Characters in Last Name and ZipPostal Code. |  | 2024-06-16 | 10:40 | 10:55
TC_36 | Verify the Checkout functionality when the user enter Numeric in Last Name, Characters in First Name and ZipPostal Code. |  | 2024-06-16 | 11:00 | 11:20
TC_37 | Verify the Checkout Functionality when the user enter Characters in First name, last name and Zippostal code. |  | 2024-06-16 | 11:35 | 11:50
TC_38 | Verify the Checkout Functionality when the user enter Numeric data in First name, last name and Zippostal code. |  | 2024-06-16 | 12:25 | 12:40
TC_39 | Verify the Checkout Functionality when the user enter Numeric data in First name and last name , character data in Zippostal code. |  | 2024-06-16 | 13:40 | 14:00
TC_40 | Verify the Checkout Functionality when the user do not enter First name, last name and Zippostal code. |  | 2024-06-16 | 15:00 | 15:20
TC_41 | Verify the Cancel button of the Checkout page is visible and clickable. |  | 2024-06-16 | 17:10 | 17:20
TC_42 | Verify the "Finish" button of Overview Page is visible and clickable. |  | 2024-06-16 | 18:00 | 18:20
TC_43 | verify the login functionality with valid details |  | 2024-06-16 | 20:00 | 20:10
TC_44 | verify the login functionality with invalid details |  | 2024-06-16 | 20:12 | 20:17
TC_45 | verify the add item to cart functionality |  | 2024-06-16 | 20:20 | 20:23
TC_46 | verify the remove item from cart functionality |  | 2024-06-16 | 20:30 | 20:35
TC_47 | verify the product details |  | 2024-06-16 | 20:39 | 20:42
TC_48 | verify the product can be sorted based on selected options |  | 2024-06-16 | 20:45 | 20:55
TC_49 | verify the checkout process |  | 2024-06-16 | 21:00 | 21:05
TC_50 | verify the empty cart message |  | 2024-06-16 | 21:07 | 21:11
TC_51 | verify the responsive design of the sauce demo |  | 2024-06-16 | 21:14 | 21:30
TC_52 | Verify the Logout Functionality of Saucedemo. |  | 2024-06-16 | 21:32 | 21:37
TC_53 | To verify menu button is clickable or not |  | 2024-06-16 | 9:10 | 9:14
TC_54 | To verify options in menu button displays or not |  | 2024-06-16 | 9:16 | 9:17
TC_55 | Verifying that clicking on "About" redirecting to about us page or not |  | 2024-06-16 | 9:20 | 9:22
TC_56 | verifying the logout functionality of application by clicking on "Logout" from the menu which logout's the user |  | 2024-06-16 | 9:30 | 9:38
TC_57 | Verifying the close button functionality to close the options |  | 2024-06-16 | 10:30 | 10:45
TC_58 | verifying that "Add to cart" button is clickable or not |  | 2024-06-16 | 14:00 | 14:07
TC_59 | Verifying the functinality of "Add to cart" by adding items to cart |  | 2024-06-16 | 14:10 | 14:25
TC_60 | Verifying that add to cart image shows count of items it contains |  | 2024-06-17 | 11:00 | 11:09
TC_61 | Verifying that items added to the cart opens product details page after clicking on the items in the cart |  | 2024-06-17 | 11:18 | 11:25
TC_62 | Verifying that the "Add to Cart" button changes to remove button after adding item to cart |  | 2024-06-17 | 11:30 | 11:37
TC_63 | Verify the login functionality when a user enter valid username and valid password. |  | 2024-06-17 | 11:40 | 11:44
TC_64 | Verify the login functionality when a user enter valid username and invalid password. |  | 2024-06-17 | 11:45 | 11:50
TC_65 | Verify the Menu icon functionality. |  | 2024-06-18 | 11:51 | 12:01
TC_66 | Verify that "All Items" is clickable in Menu. |  | 2024-06-18 | 12:05 | 12:11
TC_67 | Verify that "About" is clickable in Menu. |  | 2024-06-18 | 12:12 | 12:15
TC_68 | Checkout Button Visibility |  | 2024-06-18 | 12:20 | 12:24
TC_69 | Verify User Details Form |  | 2024-06-18 | 12:30 | 12:40
TC_70 | Verify that the filter icon is present and clickable in the product page |  | 2024-06-18 | 12:41 | 12:45
TC_71 | Verify that the products are displayed in alphabetical order from A to Z based on product name in the product page |  | 2024-06-18 | 12:47 | 12:50

## Story_Point_Effort_and_Reason
User Story1-Shamshannisha
Project Name :- | Saucedemo
Story Point :- | 1
Reason for story point :- | User is able click on product image,Remove added item from cart,open items added in cart view the product details,navigate back to product listing page
Efforts(in hours) :- | 5
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1.5 Raising Bugs:30mins
User Story2-CHANDINI APPIKONDA
Project Name :- | Saucedemo
Story Point :- | 2
Reason for story point :- | User is able to click on login button and to see home page
Efforts(in hours) :- | 5 hours
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1.5 Raising Bugs:30mins
User Story3-AjayKumar
Project Name :- | Saucedemo
Story Point :- | 3
Reason for story point :- | User is able click on login button, to see home page, Added to cart, Remove from the cart, filter option and check wheather the options are working or not.
Efforts(in hours) :- | 5hours
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1 Raising Bugs:1
User Story4- Priyanka Aute
Project Name :- | Saucedemo
Story Point :- | 3
Reason for story point :- | User is be able to enter the valid First Name, Last Name, Zippostal code, and he/she is able to click on the continue button, he/she also able to click on finish button.
Efforts(in hours) :- | 8 hours
Reason for Efforts :- | Understanding Document:1 Test cases Preparation:3.5 Test case excecution:2.5 Raising Bugs:1
User Story5- Aruna
Project Name :- | Saucedemo
Story Point :- | 5
Reason for story point :- | User is able to login,add products to the cart, remove from the cart, check the product details,sort the products,checkout process and logout
Efforts(in hours) :- | 5
Reason for Efforts :- | Understanding document:1 Test cases Preparation:2 Test case excecution:1.5 Raising Bugs:30mins
User Story5- Kalle Bhavani
Project Name :- | Saucedemo
Story Point :- | 6
Reason for story point :- | User is able click on product image, Remove added item from cart,open items added in cart view the product details,navigate back to product listing page
Efforts(in hours) :- | 6 hours
Reason for Efforts :- | Understanding document:1 Test cases Preparation:3 Test case excecution:1.5 Raising Bugs:30mins
User Story 7- Aditi Kulkarni
Project Name :- | Saucedemo
Story Point :- | 7
Reason for story point :- | check the login functionality, check Whether the options are working and user also check Whether side menu bar, User is able to filter the products based on preferences, and checkout option on cart page.
Efforts(in hours) :- | 5
Reason for Efforts :- | Test cases Preparation:3 Test case excecution:1.5 Raising Bugs:30mins

## Test report
SNO | TE NAME | TOTAL TEST CASE | PASS | FAIL | BLOCKERS | NOT EXECUTED | PASS RATIO (%) formula use : D2/C2*100 | TEST IN PROGRESS | DEV IN PROGRESS | DONE | TOTAL DEFECT
1 | Kristapadu Shamshannisha | 9 | 8 | 1 | 0 | 0 | 88% | 0 | 0 | 9 | 1
2 | CHANDINI APPIKONDA | 10 | 8 | 2 | 0 | 0 | 80% | 0 | 0 | 10 | 2
3 | Ajaykumar | 13 | 8 | 5 | 0 | 0 | 62% | 0 | 0 | 13 | 5
4 | Priyanka Aute | 10 | 5 | 5 | 0 | 0 | 50% | 0 | 0 | 10 | 5
5 | Aruna | 10 | 8 | 2 | 0 | 0 | 80% | 0 | 0 | 10 | 2
6 | Kalle Bhavani | 10 | 8 | 2 | 0 | 0 | 80% | 0 | 0 | 10 | 2
7 | Aditi | 9 | 8 | 1 | 0 | 0 | 89% | 0 | 0 | 9 | 1
TOTAL |  | 71 | 53 | 18 | 0 | 0 | 75.57 | 0 | 0 | 71 | 18